## Planilha1
Version Library – To-do
Task	Description	Status
Create VersionInfo class	VersionInfo class will replace the VersionStruct to make the struct available to C features only	0%
Remove VersionStruct dependencies	Any modification on VersionStruct demands a complete code revision when using pointers to reduce memory for dynamic components	30%
Create token conversion on “toVersionStruct3” method	Method can separate the version string components into tokens. It need to be completed to make it functional	100%
Complete toSemVerTokens	toSemVerTokens will replace all “toVersionStruct*” methods	100%
Rename methods “toVersionStruct*”	With the VersionStruct been replaced by VersionInfo, the naming used to these methods is not accurate	50%
VersionBaseClass	Provide a better way to create the version classes, sharing common components	25%
Apply inheritance on SemVer and VersionData classes	Make both classes SemVer and VersionData inherent from VersionBaseClass	0%
Add token system	Token System must offer the possibility to use a token generated list/vector and use a dictionary system to identify the correct components to simplify the creation of custom classes.	40%
Add dictionary system	Dictionary System must have the identification of components of token parts	30%
Add token mapper system	Token Mapper System must offer the components to identify the token parts with token dictionaries	30%
Apply dictionary and mapper systems for SemVer class	Make the Semantic Versioning class with full support to SemVerMapper and SemVerClassifier	60%